## Sheet1
房地产开发项目进度甘特图
编号 | 项目名称 | 开工日期 | 完工日期 | 周期 | 进度 | 第一周 | [6 empty] | 第二周 | [6 empty] | 第三周 | [6 empty] | 第三周
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | 施工准备 | 2019-09-01 | 2019-09-06 | 5 | 0%
2 | 水电改造 | 2019-09-04 | 2019-09-10 | 6 | 0%
3 | 地面工程 | 2019-09-06 | 2019-09-12 | 6 | 0%
4 | 厨房及卫生间防水 | 2019-09-04 | 2019-09-10 | 6 | 0%
5 | 闭水试验 | 2019-09-05 | 2019-09-17 | 12 | 0%
6 | 地砖铺设 | 2019-09-09 | 2019-09-20 | 11 | 0%
7 | 门安装工程 | 2019-09-13 | 2019-09-25 | 12 | 0%
8 | 衣柜安装工程 | 2019-09-16 | 2019-09-12 | -4 | 0% | [28 empty] | 本文档由稻壳儿奋斗的小青年设计制作，盗版必究。
9 | 墙面造型 | 2019-09-01 | 2019-09-10 | 9 | 0%
10 | 电视背景墙 | 2019-09-05 | 2019-09-12 | 7 | 0%
11 | 墙面批腻子 | 2019-09-07 | 2019-09-15 | 8 | 0%
12 | 墙面乳胶漆 | 2019-09-16 | 2019-09-17 | 1 | 0%
13 | 地暖设置 | 2019-09-19 | 2019-09-20 | 1 | 0%
14 | 清洁卫生 | 2019-09-23 | 2019-09-25 | 2 | 0%

## 版权说明
版权申明： Copyright Notes:
1、本文档由稻壳儿设计师"奋斗的小青年"制作完成（身份证尾号：262930）。所有文档均有合法版权证明，并委托由第三方机构负责版权维护，对于所有盗版商用必投诉追究到底，依法追究盗版者责任，以维护创作者的合法权益。 1. This document was produced by rice husk designer "struggling young people" (ID number: 262930). All documents have legitimate copyright certificates, and entrust third-party organizations to be responsible for copyright protection. All commercial piracy complaints must be investigated to the end, and pirates should be held accountable according to law in order to safeguard the legitimate rights and interests of creators. 2、本文档亦隐藏有设计师的专属印记，望慎之。 2. This document also hides the designer's exclusive imprint, so be careful. 3、如需参考本设计师的更多作品，请移步稻壳儿网站如下链接查找： 3. If you need to refer to more works of this designer, please go to the website of Rice Hull to find the following links: https://chn.docer.com/works?userid=545665384